## Sheet1
Tasks | Hours | Comments
Further data analysis through charting, research, and through tutoring sessions. | N/A | Need update from Aurora and probably meeting with Peleke on 11/27. Look at making a co2 chart similar to
Clean up folders | 1 | Chris and Aurora need to organize and clean up folders and files.
co2 chart siimilar to area plot for final presentation. | N/A | Aurora to choose countries for co2 and temperature and send to chris.
temperature chart to show multiple temperature by country as a final chart. | N/A | Look for an example chart for temperature.
Updates to the README_Project-GW.md. | 4 | This is the README_Project-GW.md file that is displayed on a page when the "About" link on the home page is clicked.
Update to the GitHub README.md | 4 | This is the file that sits in the root directory of Project-GW GitHub repo, and it will be displayed to anyone visiting the repository. This could have the same information as the "About" readme file or could contain additional details.
Make changes to home page. | 12 | * Add a d3 chart object that only displays an array of comments, questions, or tweets related to global warming. This may continuously cycle. * Add some project explanation to the bottom of the page.
Create a page or two of preparation charts such as lag plots, temperature, co2,or others. Make them like the Weather Comparison page which has 4 charts on a page or a series of pages like the 4 weather charts which have one large chart and 4 mini-charts per page. | 12 | We have the framework for each type of chart, so with the png files it will take 2-3 hours per page. With a 1-2 more hours pre page for documentation and integration.
One chart to tell the story with analysis and linkage to the preparation chart pages. | N/A | No idea what this chart will be so no estimate.
Create some PostgreSQL tables for further analysis of the data we have. |  | Depends if we need further analysis and if we have time to do the work for practice and project content.
Use Matplotlib widgets, D3+, or D3 to create an animated chart. | N/A | This is a nice to have.
Questions for Peleke on 11/30:
Choropleth world and USA maps files availability? |  | Possible world map with pop-up data like level1 d3 homework.
Temperature chart example similar to co2 example?
Histograms - what are they supposed to show us? What parameters to use in creating them? |  | For future learning and possible inclusion in a page of how we got there.
Box plots - what are they supposed to show us? What parameters to use in creating them? |  | For future learning and possible inclusion in a page of how we got there.